## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 1 | 2 | 0 | 0 | 0
| Project title: | Student Graduation Calculation and Placement Predictor |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 1 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 1 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2023-09-23 | Project Team Lead: | ABC |  |  | Dependency | 1 | 0 | 1 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 6 |  |  |  |  | 6
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Model Accuracy May Not Meet Expectations | Reduced accuracy of predictions | Implement a model retraining schedule and monitoring process to ensure ongoing performance. | Project Developer | High | 24 | Open | Risk
2 | Risk | Data Quality and Completeness Issues | Potential impact on prediction accuracy | Implement data validation and cleaning procedures | Project Developer | High | 24 | Open | Assumption
3 | Risk | Hardware failure | Disruption to project work | Implement backup and redundancy measures to minimize downtime in case of hardware failure | Project Developer | Critical | 36 | Open | Issue
5 | Assumption | The selected machine learning models will provide accurate predictions | Inaccurate predictions may impact project outcomes | Continuously monitor model performance and have a plan to retrain or adjust models if necessary. | Project Developer | Moderate | 12 | Open
6 | Dependency | Project timeline depends on external data source | Delays in project milestones | Establish regular communication with the data source provider and request timely data updates. | Project Developer | High | 24 | Open | Open
7 | Issue | Missing values in the academic year data | Delay in calculating the year of graduation | Implement data validation and imputation procedures to handle missing values | Project Developer | Moderate | 12 | Open
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24