## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Nicole Mascarenhas
PROJECT NAME: | Student Graduation Calculation and Placement Predictor
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2023-09-22
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Graduation Calculation and Placement Predictor
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Harshada Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2023-09-09 | Missing data in academic records | Data Quality Management | Yes | Implement data preprocessing procedures | Conducted data validation; handled missing data using default values | Project Developer | SOLVED | Inaccurate data initially affected model accuracy.
2 | 2023-09-16 | Model accuracy fell short of expectations | Model Development | Yes | Allow flexibility in model selection to find the most suitable one. | Model selection process made more flexible | Project Developer | SOLVED | Initial model choice didn't meet accuracy goals
3 | 2023-09-16 | Effective Meeting Attendance and Knowledge Sharing | Project Management | No | Maintain regular meetings and status updates for better communication. | Regular communication practices established | Project Developer | SOLVED | Recording meetings facilitated knowledge sharing and addressed missed meetings.