## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Progra 2023 - Machine Learning Project Schedule
|  | PROJECT START DATE | 2023-07-31
|  | Display Week Sr No | 1 | [10 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25
 | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-07-31 to 2023-10-01
1 | Initiation
1.1 |  | Identify business problem |  |  |  | Program Developer | 2023-07-31 | 2023-08-05 | 2023-07-03 | 1 | Completed | 100 | Successfully identified the key business problem
1.2 |  | Create a project Charter |  |  |  |  | 2023-08-10 | 2023-08-15 | 2023-08-12 | 3 | Completed | 100
1.3 |  | Create SRS Document |  |  | [Task 1.2] |  | 2023-08-16 | 2023-08-21 | 2023-08-18 | 2 | Completed | 100 | Dependent on the completion of the project charter.
2 | Planning
2.1 |  | Create a WBS Document |  |  |  | Program Developer | 2023-09-10 | 2023-09-15 | 2023-09-15 | 3 | Completed | 100
2.2 |  | Create the Project Schedule Document |  |  | [Task 2.1] |  | 2023-09-16 | 2023-09-19 | 2023-09-17 | 5 | Completed | 100 | Dependent on the WBS document.
2.3 |  | Create the RAID Logs |  |  | [Task 2.2] |  | 2023-08-21 | 2023-09-23 | 2023-09-23 | 5 | Completed | 100
3 | Execution
3.1 |  | Finalize design |  |  |  | Program Developer | 2023-08-26 | 2023-09-03 | 2023-09-03 | 10 | Completed | 100
3.2 |  | Build |  |  |  | Program Developer | 2023-09-03 | 2023-09-30 | 2023-09-25 | 24 | Completed | 100
3.2.1 |  |  | Data Preprocessing of Lead_Data Excel file |  |  |  | 2023-09-03 | 2023-09-07 | 2023-09-06 | 5 | Completed | 100
3.2.1.1 |  |  |  | Handling of Missing Values |  |  | 2023-09-03 | 2023-09-05 | 2023-09-05 | 2 | Completed | 100
3.2.1.2 |  |  |  | Duplicates Deletion |  |  | 2023-09-05 | 2023-09-06 | 2023-09-05 | 2 | Completed | 100
3.2.2 |  |  | Year of Graduation Calculation |  | [3.2.1.1, 3.2.1.2] |  | 2023-09-10 | 2023-09-14 | 2023-09-12 | 10 | Completed | 100
3.2.3 |  |  | Generation of New Excel file with predicted graduation year |  | [3.2.2] |  | 2023-09-14 | 2023-09-15 | 2023-09-14 | 1 | Completed | 100
3.3 |  | Data Preprocessing of Train_Data file |  |  |  | Program Developer | 2023-09-15 | 2023-09-17 | 2023-09-17 | 6 | Completed | 100
3.3.1 |  |  | Handling missing values and Removing duplicate rows. |  |  |  | 2023-09-15 | 2023-09-17 | 2023-09-17 | 2 | Completed | 100
3.3.2 |  |  | Mapping 'Placement Status' to binary labels (Placed: 1, Not placed: 0). |  | [3.3.1] |  | 2023-09-17 | 2023-09-17 | 2023-09-17 | 1 | Completed | 100
3.4 |  | Feature Selection and Encoding |  |  | [3.3.1] , [3.3.2] | Program Developer | 2023-09-17 | 2023-09-19 | 2023-09-19 | 6 | Completed | 100
3.5 |  | Model Comparison and Selection |  |  | [3.4] | Program Developer | 2023-09-19 | 2023-09-25 | 2023-09-23 | 36 | Completed | 100
3.5.1 |  |  | Model Definition |  | [3.4] |  | 2023-09-20 | 2023-09-21 | 2023-09-21 | 5 | Completed | 100
3.5.2 |  |  | Model Training and Evaluation |  | [3.4] |  | 2023-09-21 | 2023-09-22 | 2023-09-22 | 10 | Completed | 100
3.5.3 |  |  | Best Model Selection |  | [3.4] |  | 2023-09-22 | 2023-09-24 | 2023-09-23 | 8 | Completed | 100
3.5.4 |  |  | Displaying the Selected Model |  | [3.4] |  | 2023-09-24 | 2023-09-25 | 2023-09-24 | 3 | Completed | 100
3.6 |  | Testing |  |  |  | Program Developer | 2023-09-25 | 2023-09-27 | 2023-09-26 | 8 | Completed | 100
3.6.1 |  |  | Making Predictions and saving results |  | [3.5] |  | 2023-09-25 | 2023-09-27 | 2023-09-26 | 8 | Completed | 100
3.7 |  | Deploy |  |  |  | Program Developer | 2023-09-27 | 2023-09-27 | 2023-09-27 | 3 | Completed | 100
3.7.1 |  |  | Creating a short video explaining the entire process |  | 1, 2 |  | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2 | Completed | 100
4 Closure
4.1 |  | Create Lesson Learnt Document |  |  | [3.2.3], [3.5] | Program Developer | 2023-09-27 | 2023-09-29 | 2023-09-28 | 6 | Completed | 100
4.2 |  | Create Project Report |  |  | 1, 2,3 , [4.1] | Program Developer | 2023-09-27 | 2023-09-30 | 2023-09-28 | 6 | Completed | 100
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Graduation Calculation and Placement Predictor
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Predictive model for student placement and calculation function for year of graduation
PROJECT SCOPE | Developing predictive models for student placement and year of graduation based on essential features and historical data.
PROJECT START DATE | 2023-07-31
PROJECT END DATE | 2023-09-30
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2023-07-31 | 2023-08-03 | 4 | COMPLETED
| 1.2 Create a project charter |  | 2023-08-10 | 2023-08-15 | 5 | COMPLETED
| 1.3 Create SRS Document |  | 2023-08-16 | 2023-08-21 | 5 | COMPLETED
2 Planning
| 2.1 Create a WBS Document |  | 2023-09-10 | 2023-09-15 | 5 | COMPLETED
| 2.2 Create the Project Schedule Document |  | 2023-09-16 | 2023-09-19 | 4 | COMPLETED
| 2.3 Create the RAID Logs |  | 2023-08-21 | 2023-08-23 | 3 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2023-08-26 | 2023-09-03 | 9 | COMPLETED
| 3.2 Build |  | 2023-09-03 | 2023-09-30 | 28 | COMPLETED
| 3.2.1 Data Preprocessing of Lead_Data Excel file |  | 2023-09-03 | 2023-09-07 | 5 | COMPLETED
3.2.1.1 Handling of missing values in Excel file
3.2.1.2 Deletion of Duplicates
| 3.2.2 Year of Graduation Calculation |  | 2023-09-10 | 2023-09-14 | 5 | COMPLETED
| 3.2.3 Generation of New Excel file with predicted graduation year |  | 2023-09-14 | 2023-09-15 | 1 | COMPLETED
| 3.3 Data Preprocessing of Train_Data file |  | 2023-09-15 | 2023-09-17 | 3 | COMPLETED
| 3.3.1 Handling missing values and Removing duplicate rows. |  | 2023-09-15 | 2023-09-17 | 2 | COMPLETED
| 3.3.2 Mapping 'Placement Status' to binary labels (Placed: 1, Not placed: 0). |  | 2023-09-17 | 2023-09-17 | 1 | COMPLETED
| 3.4 Feature Selection and Encoding |  | 2023-09-17 | 2023-09-19 | 3 | COMPLETED
| 3.5 Model Comparison and Selection |  | 2023-09-19 | 2023-09-25 | 7 | COMPLETED
3.5.1 Model Definition
3.5.2 Model Training and Evaluation
3.5.3 Best Model Selection
3.5.4 Displaying the Selected Model
| 3.6 Testing |  | 2023-09-25 | 2023-09-27 | 3 | COMPLETED
3.6.1 Making Predictions and saving results
| 3.7 Deploy |  | 2023-09-27 | 2023-09-27 | 1 | COMPLETED
3.7.1 Creating a short video explaining the entire process
| 4 Closure |  | 2023-09-27 | 2023-09-30 | 3 | COMPLETED
| 4.1 Create Lesson Learnt Document |  | 2023-09-27 | 2023-09-27 | 2 | COMPLETED
| 4.2 Create Project Report |  | 2023-09-29 | 2023-09-30 | 1 | COMPLETED